Proof of Concept Proposal
Vegetation–Weather Outage Risk Prediction for Storm Readiness

Prepared as a focused next step following the BC Hydro presentation

1. Objective

Validate whether BC Hydro’s weather, vegetation, outage, and network data can be combined into a usable analytical dataset and used to predict elevated outage risk 24–72 hours ahead of storm events.

2. What the PoC should prove

Key data sources can be joined into one operational risk view.

Predictive analytics can identify high-risk feeders or corridors better than simple baseline methods.

Outputs can support practical decisions for storm readiness and vegetation prioritization.

3. Recommended scope

One selected operating region or service territory.

A subset of feeders, circuits, or corridors.

Historical storm events over a defined pilot period.

Feeder- or corridor-level risk scoring for a 24–72 hour pre-storm forecasting use case.

Out of scope for the PoC: province-wide rollout, real-time enterprise deployment, full digital twin implementation, underground asset intelligence, and momentary fault analytics.

4. Required data inputs

Historical outage records and, where available, restoration and crew response data.

GIS-based asset and network data, including feeder, circuit, or corridor context.

Historical weather, storm-event data, and forecast weather inputs or forecast proxies.

Vegetation inspection, patrol, treatment, and right-of-way records.

Terrain, access, and geographic hazard context where available.

5. Approach

Scoping and data discovery: confirm pilot region, required datasets, owners, granularity, and success criteria.

Data integration and feature engineering: build a pilot analytical dataset from weather, vegetation, outage, and network data.

Modeling and backtesting: build a baseline method and a predictive model, then test both against historical storm events.

Prototype outputs and evaluation: create feeder- or corridor-level risk outputs in a simple dashboard or map and assess business usefulness.

6. Deliverables

Pilot use case definition and data inventory.

Data quality and integration assessment.

Integrated pilot dataset.

Baseline versus predictive model comparison.

Historical storm-event backtesting results.

Feeder- or corridor-level risk outputs and a simple dashboard or map-based prototype.

Final findings, limitations, and recommendation for the next implementation step.

7. Indicative timeline

Recommended duration: 10–12 weeks (up to 14 weeks if internal data access is delayed).

| Phase | Duration | Activities |
| --- | --- | --- |
| 1. Scoping and data discovery | 1–2 weeks | Confirm pilot region, data owners, access, granularity, and success criteria |
| 2. Data integration and preparation | 2–3 weeks | Profile sources, clean and align datasets, define analytical data model, engineer features |
| 3. Modeling and backtesting | 3–4 weeks | Build baseline and predictive model, test against historical storm events, compare performance |
| 4. Prototype outputs and review | 2–3 weeks | Create dashboard/map outputs, review usability, summarize findings and recommendations |

8. Indicative team structure

A focused PoC needs a small cross-functional team. Several responsibilities may be combined, but these capabilities should be covered:

- Data Scientist / ML Lead: analytical design, feature engineering, baseline and predictive modeling, risk-score logic, model evaluation, backtesting, and interpretation of results.

- Data Engineer / AI Developer: data ingestion, cleaning, integration, analytical dataset preparation, reusable scoring workflows, model packaging, and technical implementation support.

- Business Analyst: requirements gathering, discovery support, current-state workflow understanding, success criteria, user needs, and business-value framing, including reliability and operational indicators such as SAIDI, SAIFI, CAIDI, vegetation spend, outage impact, and restoration effort.

- GIS / Geospatial Specialist: spatial alignment, feeder/corridor logic, GIS layers, geospatial joins, map-based risk outputs, and validation of location-based assumptions.

- Dashboard / Front-End Developer: prototype dashboard, map views, risk ranking tables, user-facing outputs, and visualization of risk drivers and backtesting results.

- QA / Test Support: validation of data transformations, risk outputs, dashboard logic, test scenarios, and consistency of prototype behaviour.

- Project Manager / Delivery Lead: scope management, schedule coordination, risk tracking, stakeholder alignment, and delivery governance.

- Utility SME / Business Stakeholder: operational validation, workflow context, outage/vegetation process knowledge, success criteria review, and feedback on whether outputs are useful for storm readiness and planning.

Indicative effort estimate

For planning purposes, a protected estimate for a focused 10–12 week PoC is approximately 920 hours.

| Role | Estimated hours |
| --- | --- |
| Data Scientist / ML Lead | 210 |
| Project Manager / Delivery Lead | 80 |
| Data Engineer / AI Developer | 240 |
| Business Analyst | 90 |
| GIS / Geospatial Specialist | 120 |
| QA / Test Support | 70 |
| Dashboard / Front-End Developer | 110 |
| Total Fujitsu effort | 920 h |

Client-side Utility SME / Business Stakeholder time is not included in Fujitsu delivery hours unless requested separately.

9. Success criteria

Core pilot data sources can be integrated at useful operational granularity.

Model outputs identify elevated outage risk more effectively than simple baseline rules.

Outputs are interpretable and usable by operations and planning stakeholders.

A credible path exists from PoC to a broader pilot or operational deployment.

10. Key risks and assumptions

Data quality, structure, and operational granularity may vary across sources.

Historical forecast data may be limited and may require proxy treatment.

Vegetation records may differ in completeness by region.

Business validation is required in addition to model performance metrics.

11. Recommended next step

Confirm the pilot region, identify data owners for required sources, and align on PoC success criteria before starting technical work.