# Project Overview
BC Hydro Vegetation–Weather Outage Risk Analytics

Prepared to support internal planning for proof of concept, pilot delivery, and broader project execution

# 1. Executive Summary

This project is intended to help BC Hydro improve storm readiness, outage prediction, and vegetation-risk prioritization by combining weather, vegetation, outage history, and network context into one operational analytics capability.

The recommended delivery path is phased. Phase 1 is a focused proof of concept to validate data integration, predictive usefulness, and operational relevance. If successful, Phase 2 expands into a business pilot with broader stakeholder use, repeatable data pipelines, and decision-support outputs. Phase 3 would be an operational scale-up that moves the capability toward a digital twin-style decision framework for weather, vegetation, network conditions, and outage risk.

This overview is intentionally focused on project scope, structure, timeline, roles, dependencies, and delivery shape. It does not address pricing or commercial terms.

# 2. Project Objective and Business Value

| Area | Summary |
| --- | --- |
| Objective | Create a practical analytics capability that identifies where weather and vegetation are most likely to cause outages, supports better pre-staging and operational response, and improves vegetation-related planning decisions. |
| Immediate value | Improve 24–72 hour storm readiness, feeder or corridor risk visibility, and operational prioritization before and during storm events. |
| Longer-term value | Support risk-based vegetation strategy, resilience investment decisions, and evolution toward a digital twin-style operational view of the network and environmental risk drivers. |
| Business-value indicators | Support future assessment of reliability and operational value through indicators such as SAIDI, SAIFI, CAIDI, customer interruption minutes, vegetation prioritization, restoration effort, crew staging, and resilience investment decisions. |

# 3. Proposed Scope

## In scope

Vegetation–weather outage risk as the primary use case

Historical outage, weather, vegetation, and network data integration

Feeder-, circuit-, or corridor-level risk scoring based on available operational granularity

Backtesting against historical storm events

Prototype decision-support outputs such as risk maps, ranked lists, and simple dashboards

## Out of scope in early phases

Province-wide enterprise rollout

Full real-time production integration across all systems

A complete grid-wide digital twin implementation from day one

Secondary use cases such as underground asset intelligence or momentary fault analytics as primary workstreams

# 4. Delivery Approach and Indicative Timeline

Recommended overall approach:

Phase 1 – Proof of Concept: validate feasibility, integration, predictive value, and operational relevance

Phase 2 – Business Pilot: expand scope, improve repeatability, strengthen user workflows, and confirm stakeholder fit

Phase 3 – Scaled Implementation: productionize the capability, strengthen governance, and evolve toward a digital twin-style decision framework

| Phase | Purpose | Indicative Duration | Typical Outputs |
| --- | --- | --- | --- |
| Phase 1: PoC | Prove that pilot-region data can be integrated and used for meaningful storm-risk prediction. | 10–12 weeks (allow up to 14 with data-access delays) | Data inventory; integrated analytical dataset; baseline vs model comparison; historical backtesting; prototype dashboard or map; recommendation for next step |
| Phase 2: Pilot | Extend to a broader operating context with more users, better pipelines, and clearer operational playbooks. | 3–6 months | Improved data pipelines; broader regional coverage; user-tested decision support; KPI definition; pilot operating model |
| Phase 3: Scale-up | Operationalize the capability and connect it into broader planning and operational workflows. | 6–12+ months (depending on integration scope) | Repeatable production workflows; governance model; expanded coverage; scenario analysis; digital twin-style operational view |

# 5. Team Structure and Roles

The work should be delivered by a small cross-functional team rather than by a single specialist. For the proof of concept, several roles may be combined, but the capabilities below should be covered.

| Role | Primary responsibilities | Notes |
| --- | --- | --- |
| Data Scientist / ML Lead | Analytical design, feature engineering, baseline and predictive models, evaluation, interpretation | Core analytical role |
| Data Engineer / AI Developer | Data ingestion, cleaning, joins, analytical dataset preparation, reusable scoring workflows, model packaging | Combines DE + AI developer responsibilities for lean PoC |
| Business Analyst | Requirements, workflow discovery, success criteria, stakeholder needs, business-value framing, SAIDI / SAIFI / CAIDI context | Important now because financial and reliability value are part of the discussion |
| GIS / Geospatial Specialist | Spatial alignment, corridor/feeder logic, geospatial feature engineering, spatial validation | Critical because the use case is location-dependent |
| Dashboard / Front-End Developer | Prototype dashboard, map views, ranking tables, user-facing outputs | Needed for reviewable PoC outputs |
| QA / Test Support | Data validation, output consistency checks, traceability, scenario testing | Part-time but useful |
| Project Manager / Delivery Lead | Scope, schedule, risks, stakeholder coordination, governance | Keeps delivery controlled |
| Utility SME / Business Stakeholder | Operational validation, workflow context, success criteria, review of outputs | Usually BC Hydro participation |

# 6. Dependencies, Risks, and Assumptions

## Key dependencies

Confirmation of pilot region and operational use case

Access to required outage, weather, vegetation, and network data

Availability of useful join keys and sufficient operational granularity

Business stakeholder participation for validation and feedback

## Main risks

Data quality or structure may vary across sources and systems

Historical forecast data may be incomplete or require proxy treatment

Vegetation records may differ in detail and quality by region

Operational usefulness must be validated with end users, not only through model metrics

## Working assumptions

A PoC is intended to prove feasibility and business value, not solve the full enterprise problem

A lean cross-functional team is available for the pilot period

Success criteria are agreed before technical work begins

# 7. Success Criteria and Next Steps

Core pilot data sources can be integrated at useful operational granularity

Model outputs identify elevated outage risk more effectively than simple baseline rules

Outputs are interpretable and useful for operations and planning stakeholders

A credible path exists from PoC to broader pilot and scaled implementation

Recommended next step: Confirm the pilot region, identify data owners, align on success criteria, and decide the lean delivery team needed to start Phase 1.